## Public
Clause |  | Task |  | Description | Priority | Affect to scores | Lead |  |  | Completed | Actions | Milestones | Updated Milestones 2018 | 2018 | [11 empty] | 2019 | [11 empty] | 2020
[7 empty] | KT | Fishery | Other |  |  |  |  | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December
Management | M2 | 1 | Support to improve compliance | Identify and source means (resources and funding) to fill gaps identified Support projects for compliance improvement | Medium | Pass | X |  |  | In Progress | • Identify and source means (resources and funding) to fill gaps identified • Support projects for compliance improvement | Year 1 Identify gaps Year 2 Find resources and funding to fill gaps Year 3 Implement actions to fill gaps Year 4 See a marked improvement in compliance
|  | 1.1 | Analysis and implementation of an effective compliance system | A programme of observers or other data collection on board selected vessels to collect information on discards and interactions with endangered species. Evaluation of the likely impact of the fishery on the ecosystem in Mauritania, via an ecosystem model (e.g. based on Guénette et al., 2014). | Low | Pass | X | X |  | In Progress | • Evaluate with stakeholders how these gaps could best be filled (e.g. support to existing compliance structures vs. development of new methods) • Evaluate likely issues for compliance / enforcement in relation to proposed new measures required under new objectives / management plans • Evaluate for the small pelagic fishery specifically the key issues with compliance / enforcement in relation to existing laws, working with stakeholders | Year 1 Evaluate with stakeholders how these gaps could best be filled (e.g. support to existing compliance structures vs. development of new methods) Evaluate likely issues for compliance / enforcement in relation to proposed new measures required under new objectives / management plans Evaluate for the small pelagic fishery specifically the key issues with compliance / enforcement in relation to existing laws, working with stakeholders Year 2 Attempt to address these issues and implement actions to address shortcomings Year 3 Attempt to address these issues and implement actions to address shortcomings
|  | 1.2 | Development of arrêtés and other legislative instruments to bring into force relevant legislation and policies | Although the legal and policy framework is satisfactory, its application on the ground is lacking; in particular in relation to the Sectoral Fishing Strategy (2015-19) which puts in place a quota system from 2016. The implementation of the legal framework needs to be supported by an effective monitoring, control and sanctions system. Improved application of the existing national legislation, after regional harmonisation as far as possible. Priority should be given in particular to the implementation of the new sectorial fishing strategy 2015-2019. | Medium | Pass | X | X | X | To be done | • Identify resources required to implement legislation on the ground and support the Ministry in identifying resources where necessary • Work with and support Ministry to develop suitable arrêtés and other legislative instruments to fill gaps as required, in consultation with stakeholders, e.g. via organisation of stakeholder workshops, support for legal and drafting • Work with the Ministry to evaluate gaps in implementation of legislation | Year 1 Engage with the ministry to identify steos Year 2 Support the ministry in the development of arrêtés Year 3 Participate in stakeholder meetings Year 4 Assist and support the ministry in implementation
|  | 1.3 | Promote bilateral or multilateral agreements on management questions where necessary | Although the legal and policy framework is satisfactory, its application on the ground is lacking; in particular in relation to the Sectoral Fishing Strategy (2015-19) which puts in place a quota system from 2016. Improved application of the existing national legislation, after regional harmonisation as far as possible. Priority should be given in particular to the implementation of the new sectorial fishing strategy 2015-2019. | High | Pass | X | X |  | In Progress | • Where the appropriate management level seems to be national, management plans should be developed at national level • Work with the Ministry in Mauritania to bring forward issues relevant to the fishery at the relevant regional level; this could be done via the above regional body, or if too early via e.g. sponsoring regional workshops, working directly with Senegal • Evaluate options for national-level biomass indicators for regional stocks, such that even in the absence of formal regional management (e.g. as an interim measure) Mauritania and the other countries in the region are able to evaluate an appropriate share • Evaluate with regional scientists (e.g. IMROP and collaborators in other countries, or via FAO/COPACE) the geographical level required for management of each stock: e.g. sardinella appear to be regional shared stocks with Mauritania and Senegal | Year 1 Evaluate with regional scientists (e.g. IMROP and collaborators in other countries, or via FAO/COPACE) the geographical level required for management of each stock: e.g. sardinella appear to be regional shared stocks with Mauritania and Senegal Evaluate options for national-level biomass indicators for regional stocks, such that even in the absence of formal regional management (e.g. as an interim measure) Mauritania and the other countries in the region are able to evaluate an appropriate share Year 2 Work with the Ministry in Mauritania to bring forward issues relevant to the fishery at the relevant regional level; this could be done via the above regional body, or if too early via e.g. sponsoring regional workshops, working directly with Senegal Year 3 Work with the Ministry in Mauritania to bring forward issues relevant to the fishery at the relevant regional level; this could be done via the above regional body, or if too early via e.g. sponsoring regional workshops, working directly with Senegal Year 4 Work with the Ministry in Mauritania to bring forward issues relevant to the fishery at the relevant regional level; this could be done via the above regional body, or if too early via e.g. sponsoring regional workshops, working directly with Senegal
|  | 1.4 | Support an appropriate regional body in developing the regional-level management of small pelagic stocks | Creation and/or support and development of regional organisation for the management of trans-boundary pelagic fish stocks in the region. This could be the Commission Sous-Régionale des Pêches (although Morocco is not member of this organisation) or another body, for instance under the auspices of ATLAFCO (the Ministerial Conference on Fisheries Cooperation Among African States Bordering the Atlantic, best known as COMHAFAT, Conférence ministérielle sur la coopération halieutique entre les états africains riverains de l’Océan Atlantique). Either way, the main role of this commission would be to adopt robust regional-level management for each species, based on the recommendation of the regional scientific community (FAO/COPACE), and to decide how to share quotas, capacity reductions or other measures between the different countries of the region. If formal regional-level management appears likely to be unsuccessful within the FIP timeframe, it would also be possible to work for sardinella specifically under a more ad hoc framework of management coordination between Mauritania and Senegal (accounting for 80-90% of the sardinella catch) with if possible Morocco (accounting for nearly all the remainder). | High | Pass | X | X |  | In Progress | • Apply to attend organisation meetings as an observer; put forward observer / stakeholder comments where permitted to support regional management • Put forward proposals where relevant to solve issues that arise which may block the progress of the organisation • Lobby authorities in all relevant countries to promote the development of relevant structures and procedures in the organisation (e.g. agreement of procedures, terms of reference, organisation, budget etc.) • Identify the most suitable regional body to act as a management agency for the stocks | Year 1 Apply to attend organisation meetings as an observer; put forward observer / stakeholder comments where permitted to support regional management Put forward proposals where relevant to solve issues that arise which may block the progress of the organisation Year 2 Lobby authorities in all relevant countries to promote the development of relevant structures and procedures in the organisation (e.g. agreement of procedures, terms of reference, organisation, budget etc.) Identify the most suitable regional body to act as a management agency for the stocks Year 3 Lobby authorities in all relevant countries to promote the development of relevant structures and procedures in the organisation (e.g. agreement of procedures, terms of reference, organisation, budget etc.) Year 4 Lobby authorities in all relevant countries to promote the development of relevant structures and procedures in the organisation (e.g. agreement of procedures, terms of reference, organisation, budget etc.)
|  | 1.5 | Improve fishery-dependent sampling | Management of the fishery needs to take uncertainty into account, particularly where information is lacking, and should set target biomass levels and fishing strategies which take the needs of the wider ecosystem into account. Improved compliance with this part of the standard mainly arises indirectly through actions in other more specific areas (e.g. improved data collection, a stronger stock management framework. The data needed to evaluate stock status is not being collected: improved assessment of biomass is needed (e.g. via acoustic surveys) as well as better fishery-dependent data (catch, discards, size-frequencies) for different fleet segments. Better information is needed to comply | Medium | Pass | X |  |  | To be done | • Adapt sampling protocol as required based on the below • Evaluate resources available for sampling in relation to sampling required by IMROP and FAO/COPACE for improved stock assessment; develop funding proposal to improve sampling coverage if necessary • In consultation with FAO/COPACE if necessary, evaluate protocol for size-frequency and other sampling of catches e.g. coverage of various fleet segments, assessment of sampling frequency vs sample size | Year 1 Evaluate resources available for sampling in relation to sampling required by IMROP and FAO/COPACE for improved stock assessment; develop funding proposal to improve sampling coverage if necessary Year 2 In consultation with FAO/COPACE if necessary, evaluate protocol for size-frequency and other sampling of catches e.g. coverage of various fleet segments, assessment of sampling frequency vs sample size Year 3 Adapt sampling protocol as required
|  | 1.6 | Improve the acoustic survey frequency / methodology | The data needed to evaluate stock status is not being collected: improved assessment of biomass is needed (e.g. via acoustic surveys) as well as better fishery-dependent data (catch, discards, size-frequencies) for different fleet segments. Better information is needed to comply with Part B1 and to apply Part B2 to management. | Medium | Pass | X |  |  | To be done | • Assess options for analysis of survey data and develop funding proposals for support of data analysis and preparation if necessary • Develop funding proposals to cover costs of improved survey coverage (e.g. via EU fisheries agreements or other options) • Assess requirements and costs for filling key gaps in survey coverage and frequency, as well as options (e.g. vessels available) • Evaluate with regional scientists suitability of existing surveys and key gaps (e.g. via FAO/COPACE or in separate workshop) | Year 1 Assess options for analysis of survey data and develop funding proposals for support of data analysis and preparation if necessary Year 2 Develop funding proposals to cover costs of improved survey coverage (e.g. via EU fisheries agreements or other options) Assess requirements and costs for filling key gaps in survey coverage and frequency, as well as options (e.g. vessels available) Year 3 Evaluate with regional scientists suitability of existing surveys and key gaps (e.g. via FAO/COPACE or in separate workshop)
Category B | B | 2 | Management plan for the sardinella fishery | The two sardinella stocks are shared across the region (Mauritania, Senegal, Gambia and Morocco), while the geographical boundaries of the obo stock are less clear. Although there is assessment of the stocks at regional level via COPACE, there is no regional-level management, as would be required for high compliance. Creation and/or support and development of regional organisation for the management of trans-boundary pelagic fish stocks in the region. This could be the Commission Sous-Régionale des Pêches (although Morocco is not member of this organisation) or another body, for instance under the auspices of ATLAFCO (the Ministerial Conference on Fisheries Cooperation Among African States Bordering the Atlantic, best known as COMHAFAT, Conférence ministérielle sur la coopération halieutique entre les états africains riverains de l’Océan Atlantique). Either way, the main role of this commission would be to adopt robust regional-level management for each species, based on the recommendation of the regional scientific community (FAO/COPACE), and to decide how to share quotas, capacity reductions or other measures between the different countries of the region. If formal regional-level management appears likely to be unsuccessful within the FIP timeframe, it would also be possible to work for sardinella specifically under a more ad hoc framework of management coordination between Mauritania and Senegal (accounting for 80-90% of the sardinella catch) with if possible Morocco (accounting for nearly all the remainder). The Ministry explained about ongoing modernisation of legislation and will present on this at the FIP meeting in March. This will include an evaluation of the regulations (not independent) and Dr. Jo Gascoigne can review the results and compare it to Dr. Pierre Freon’s assessment. The actions include consulting with FAO/COPACE and/or regional scientific bodies, to assess status of both stocks in relation to current regional objectives and developing a management plan for the Mauritania sardinella fishery, including appropriate measures for each fleet segment to deliver regional and associated national stock objectives, as well as socio-economic objectives if desired. | High | Pass | X |  |  | In Progress | • Implement the management plan via suitable decrees of application, arrêtés or other legislative instruments, as well as a suitable administrative framework and resources • Within this management plan, define a harvest strategy with appropriate reference points (target, limit and precautionary ones) for the two species • Develop a management plan for the Mauritania sardinella fishery, including appropriate measures for each fleet segment to deliver regional and associated national stock objectives, as well as socio-economic objectives if desired • Evaluate catches and/or fishing capacity in Mauritania in relation to sardinella resources available to the Mauritanian fishery (including piroguiers, larger vessels and foreign licensing), whether catch and/or capacity reduction is required • Develop appropriate national-level objectives for the stock which can support the delivery of regional objectives • In consultation with FAO/COPACE and/or regional scientific bodies, assess stock status in relation to current regional objectives | Year 1 Analyse the current management plan and data gaps. Ealuate catches made by the fishery and beyond Year 2 Develop a management plan for the Mauritania sardinella fishery, including appropriate measures for each fleet segment to deliver regional and associated national stock objectives, as well as socio-economic objectives if desired Year 3 Develop appropriate national-level objectives for the stock which can support the delivery of regional objectives In consultation with FAO/COPACE and/or regional scientific bodies, assess stock status in relation to current regional objective
|  | 2.1 | Defining the sardinella stock | The data needed to evaluate stock status is not being collected: improved assessment of biomass is needed (e.g. via acoustic surveys) as well as better fishery-dependent data (catch, discards, size-frequencies) for different fleet segments. Funding and implementation of improved data collection, particularly in relation to the total and spawning biomass of the different stocks, fish size frequencies and catch per species (including discards) for the different segments of the fishery in the different countries of the region. | High | Pass | X |  |  | In Progress | • Support additional data collection if required to define suitable stock or management unit boundaries • Evaluate stock definitions of the sardinella stocks | Year 1 Evaluate current stock definitions, data and identify gaps Year 2 Implement additional data collection as necessary Year 3 Implement additional data collection as necessary Year 4 Evaluate data collection
|  | 2.2 | Analyse and understand the Cunene horse mackerel stock | For Trachurus trecae, despite the increase in catches observed in 2010, the stock situation has greatly deteriorated. The FIP will advocate for the increasing trend of the Russian CPUEs to be analysed taking into account the stock distribution changes in the subregion and work towards reducing fishing effort by 30 percent. | High | Pass | X |  |  | To be done | • Support additional data collection if required to define suitable stock or management unit boundaries • Advocate for increased work into stock definition and distribution • Evaluate stock definitions of the horse mackerel stocks | Year 2 Implement additional data collection as necessary Year 3 Analyse stock definitions Year 4 Evaluate data collection
|  | 2.3 | Increase sampling of Chub Mackerel | In the Mauritanian fishery, sampling is carried out on board pelagic trawlers by IMROP scientists and Russian observers and has been declining since 2006. This needs to be increased along with the identification of mackerel using genetic and morphometric methods. | High | Pass | X |  |  | To be done | • Work to increase data for chub mackerel • Advocate for more advanced identification techniques | Year 2 Work to increase data for chub mackerel Year 3 Advocate for more advanced identification techniques Year 4 Evaluate results
|  | 2.4 | Management plan for the obo fishery | Management of the fishery needs to take uncertainty into account, particularly where information is lacking, and should set target biomass levels and fishing strategies which take the needs of the wider ecosystem into account. Improved compliance with this part of the standard mainly arises indirectly through actions in other more specific areas (e.g. improved data collection, a stronger stock management framework); specific activities to deal with Part C are therefore not proposed in this workplan. | High | Pass | X |  |  | In Progress | • Implement the management plan via suitable decrees of application and arrêtés or other legislative instruments, as well as a suitable administrative framework and resources • Within this management plan, define a harvest strategy with appropriate reference points (target, limit and precautionary ones) for the two species • Develop a management plan for the obo fishery consistent with the sectorial strategy, including agreed objectives and measures for each fleet segment to deliver stock objectives, as well as socio-economic objectives and actions if desired • If capacity / catch reduction is required, work with stakeholders from all fishery segments to assess and agree a management approach consistent with agreed objectives • Support the Ministry and scientists in evaluating catches and/or capacity in relation to obo resources available to the fishery (including piroguiers, larger vessels and foreign licensing), whether catch and/or capacity reduction is required • With IMROP, assess stock status of obo in Mauritania in relation to objectives • Work with other stakeholders to support a process for the development of suitable objectives for the obo stock at Mauritanian level | Year 1 If capacity / catch reduction is required, work with stakeholders from all fishery segments to assess and agree a management approach consistent with agreed objectives Year 2 Work with other stakeholders to support a process for the development of suitable objectives for the obo stock at Mauritanian level Support the Ministry and scientists in evaluating catches and/or capacity in relation to obo resources available to the fishery (including piroguiers, larger vessels and foreign licensing), whether catch and/or capacity reduction is required. With IMROP, assess stock status of obo in Mauritania in relation to objectives Year 3 Develop a management plan for the obo fishery consistent with the sectorial strategy, including agreed objectives and measures for each fleet segment to deliver stock objectives, as well as socio-economic objectives and actions if desired Year 4 Implement the management plan via suitable decrees of application and arrêtés or other legislative instruments, as well as a suitable administrative framework and resources
|  | 2.5 | Advocate for the reduction of both effort and catch for the Atlantic Horse Mackerel is required. | The effort and catch of Atlantic horse mackerel is noted as being too high and requiring reduction. However, the lack of management required is absent. The fishery will advocate for stronger management and enforcement of the stock. | High | Pass | X | X |  | To be done | • Evaluate the management of Atlantic horse mackerel • Advocate for stronger management • Engage and assist with stronger management and enforcement | Year 2 Assess the total overlap of stock Advocate for stronger management Engage and assist with stronger management and enforcement Year 3 Advocate for stronger management Engage and assist with stronger management and enforcement Year 4 Advocate for stronger management Engage and assist with stronger management and enforcement
Category D | D | 3 | Improve management of False Scad | Overlap of adult species range with the fishery is high which requires improved management to ensure the long term sustainbility of the stock. | High | Pass | X | X |  | To be done | • Find required missing data for the preassessment • Assess total overlap and stock • Engage with relevant management and advocate for stronger management | Year 2 Assess the current stock and map overlap Assess the current management measures Advocate for stronger management measures Year 3 Advocate for stronger manamgement measures Year 4 Advocate for stronger manamgement measures
Further Impacts | F1 | 4 | Data collection on discards and endangered species interactions | A programme of observers or other data collection on board selected vessels to collect information on discards and interactions with endangered species. Evaluation of the likely impact of the fishery on the ecosystem in Mauritania, via an ecosystem model (e.g. based on Guénette et al., 2014). | High | Pass | X | X |  | To be done | • Work with the Ministry to implement additional management measures for bycatch or endangered species protection, if necessary according to the data • Work with IMROP to analyse data • Implement an observation scheme, working with cooperative skippers • Work with cooperative skippers to assess the best way of collecting data from Mauritanian vessels from different fleets; e.g. observers, cameras, other methods; identify funding sources • Support IMROP in the analysis of existing observer data (EU), if not already done | Year 1 Improve the quality and quantity of data through implementing new techniques in the fleet and beyond Year 2 Support IMROP to analyse data Work with the ministry to implement management measures Year 3 Implement measures Year 4 Analyse impacts
| F3 | 4.1 | Evaluation of the impact on the ecosystem | IMROP intend to carry out an analysis of data collection and create a plan for the ecosystem modelling project. This will be presented at the FIP meeting in March. It might look something like the Moroccan modelling for key LTL and we could invite Dr. Sylvie to comment on it. This action will involve working with IMROP to support work on ecosystem impacts of the fishery in Mauritania. | High | Pass | X | X |  | To be done | • Incorporate the results of the study into the development of objectives and management plans, so that ecosystem impacts are restrained at an appropriate level • Work with IMROP to support work on ecosystem impacts of the fishery in Mauritania; e.g. supporting work to develop the existing ecosystem model, supporting joint funding proposals with other regional or international groups or by some other suitable | Year 1 Collect data and analyse the impacts the fishery has on the ecosystem Year 2 Make any necessary changes within the fishery, such as gear type or timing of fishing Year 3 Work with IMROP to support work on ecosystem impacts of the fishery in Mauritania Year 4 Analyse changes made and assess effectiveness
Other | na | 5 | Identify and coordinate with other relevant projects | Engaging with relevant organisations and groups such as ISSF will provide the FIP to progress at a faster rate to reach the desired goal. | Medium | Pass | X |  |  | In Progress | • Assess relevant fisheries carrying out similar work in the area • Engage with identified projects • Work together to meet shared targets | Year 1 Engage with relevant organisations such as ISSF Year 2 Conduct a review of other relevant organisations Year 3 Conduct a review of other relevant organisations
| na | 5.1 | Identify any social issues within the fishery | In addition to the scored criteria listed above, IFFO ask applicants to commit to ensuring that vessels operating in the fishery adhere to internationally recognised guidance on human rights. They must also commit to ensuring there is no use of enforced or unpaid labour in the fleet(s) operating upon the resource. We must analyse the fishery and implement any necessary changes. | Medium | Pass | X |  |  | In Progress | • Assess social components within the fishery • Implement any necessary changes • Monitor and report on these actions | Year 2 Assess social components within the fishery Implement any necessary changes Year 3 Monitor and report on these actions

## Benchmarked Scoring
Clause | Requirement | Description | Score | MSC Indicator (s) | MSC Equivalence Score | Comments
M1 | M1.1 | There is an organisation responsible for managing the fishery | Y | 3.1.1 | >80 | Not direct, IFFO needs more to meet MSC
| M1.2 | There is an organisation responsible for collecting data and assessing the fishery | Y | 2.1.2, 3.2.4 | 60-79 | Not direct, IFFO needs more to meet MSC
| M1.3 | Fishery management organisations are publically committed to sustainability | Y | 3.2.1 | >80 | Direct translation
| M1.4 | Fishery management organisations are legally empowered to take management actions | Y | 3.1.1 | >80 | Direct translation
| M1.5 | There is a consultation process through which fishery stakeholders are engaged in decision-making | Y | 3.1.2 | 60-79 | Not direct, IFFO needs more to meet MSC
| M1.6 | The decision-making process is transparent, with processes and results publically available | Y | 3.2.2 | >80 | Direct translation
M2 | M2.1 | There is an organisation responsible for monitoring compliance with fishery laws and regulations | Y | 3.1.1 | >80 | Direct translation
| M2.2 | There is a framework of sanctions which are applied when laws and regulations are discovered to have been broken | Y | 3.2.3 | >80 | Direct translation
| M2.3 | There is no substantial evidence of widespread non-compliance in the fishery, and no substantial evidence of IUU fishing | N | 3.2.3 | <60 | Direct translation
| M2.4 | Compliance with laws and regulations is actively monitored, through a regime which may include at-sea and portside inspections, observer programmes, and VMS. | N | 3.2.3 | <60 | Direct translation
B1 | Round Sardinella | Table Ba | N | 1.1.1, 1.2.3, 2.1.1 | >60 | Limited P1 and primary, IFFO based on fishing mortality and ref points
B1 | Cunene Horse Mackerel | Table Ba | N | 1.1.1, 1.2.3, 2.1.1 | >60 | Limited P1 and primary, IFFO based on fishing mortality and ref points
B1 | Flat Sardinella | Table Ba | N | 1.1.1, 1.2.3, 2.1.1 | >60 | Limited P1 and primary, IFFO based on fishing mortality and ref points
B1 | Chub Mackerel | Table Ba | N | 1.1.1, 1.2.3, 2.1.1 | >60 | Limited P1 and primary, IFFO based on fishing mortality and ref points
B1 | European Pilchard | Table Ba | Y | 1.1.1, 2.1.1 | >80 | Limited P1 and primary, IFFO based on fishing mortality and ref points
B1 | Atlantic Horse Mackerel | Table Ba | N | 1.1.1, 1.2.3, 2.1.1 | >60 | Limited P1 and primary, IFFO based on fishing mortality and ref points
B1 | Bonga | Table Bb | N | 1.1.1, 1.2.3, 2.1.1 | >60 | Limited P1 and primary, IFFO based on fishing mortality and ref points
D1 | False Scad | PSA | N | P2 | <60 | As per RBF scoring Some quantitative information is adequate to assess PSA
D1 | European Anchovy | PSA | Y | P2 | 60-79 | As per RBF scoring - 2.1.3 = >80
D4 | D4.1 | The potential impacts of the fishery on this species are considered during the management process, and reasonable measures are taken to minimise these impacts. | N | 2.5.2 | <60 | Ecosystem based indicators
| D4.2 | There is no substantial evidence that the fishery has a significant negative impact on the species. | N | 2.5.1 | <60 | Ecosystem based indicators
F1 | F1.1 | Interactions with ETP species are recorded. | N | 2.3.3 | <60 | Direct translation
| F1.2 | There is no substantial evidence that the fishery has a significant negative effect on ETP species. | Y | 2.3.1 | >80 | Direct translation
| F1.3 | If the fishery is known to interact with ETP species, measures are in place to minimise mortality. | Y | 2.3.2 | >80 | Direct translation
F2 | F2.1 | Potential habitat interactions are considered in the management decision-making process. | Y | 2.4.2, 2.4.3 | >80 | Direct translation
| F2.2 | There is no substantial evidence that the fishery has a significant negative impact on physical habitats. | Y | 2.4.1 | >80 | Direct translation
| F2.3 | If the fishery is known to interact with physical habitats, there are measures in place to minimise and mitigate negative impacts. | Y | 2.4.2 | >80 | Direct translation
F3 | F3.1 | The broader ecosystem within which the fishery occurs is considered during the management decision-making process. | N | 2.5.2 | <60 | Direct translation
| F3.2 | There is no substantial evidence that the fishery has a significant negative impact on the marine ecosystem. | N | 2.5.1, 2.5.3 | <60 | Lacking complete scoring of information, presumed through needing evidence
| F3.3 | If one or more of the species identified during species categorisation plays a key role in the marine ecosystem, additional precaution is included in recommendations relating to the total permissible fishery removals. | Y | 2.5.2, 1.2.2 | <60 | Direct translation
Social | na | In addition to the scored criteria listed above, applicants must commit to ensuring that vessels operating in the fishery adhere to internationally recognised guidance on human rights. They must also commit to ensuring there is no use of enforced or unpaid labour in the fleet(s) operating upon the resource. | N | na | na | No social elements currently in the MSC Standard

## MSC Scoring
Principle | Component | Performance Indicator | Round Sardinella | Cunene Horse Mackerel | Flat Sardinella | Chub Mackerel | European Pilchard | Atlantic Horse Mackerel | Bonga
1 | Outcome | 1.1.1 Stock status | <60 | <60 | <60 | <60 | >80 | <60 | <60
|  | 1.1.2 Stock rebuilding | <60 | <60 | <60 | <60 | >80 | <60 | <60
| Management | 1.2.1 Harvest Strategy | Not scored | Not scored | Not scored | Not scored | Not scored | Not scored | Not scored
|  | 1.2.2 Harvest control rules and tools | <60 | <60 | <60 | <60 | <60 | <60 | <60
|  | 1.2.3 Information and monitoring | 60-79 | 60-79 | 60-79 | 60-79 | 60-79 | 60-79 | 60-79
|  | 1.2.4 Assessment of stock status | Not scored | Not scored | Not scored | Not scored | Not scored | Not scored | Not scored
2 | Primary species | 2.1.1 Outcome | <60
|  | 2.1.2 Management | 60-79
|  | 2.1.3 Information | 60-79
| Secondary species | 2.2.1 Outcome | <60
|  | 2.2.2 Management | Not scored
|  | 2.2.3 Information | 60-79
| ETP species | 2.3.1 Outcome | >80
|  | 2.3.2 Management | >80
|  | 2.3.3 Information | <60
| Habitats | 2.4.1 Outcome | >80
|  | 2.4.2 Management | >80
|  | 2.4.3 Information | 60-79
| Ecosystem | 2.5.1 Outcome | <60
|  | 2.5.2 Management | <60
|  | 2.5.3 Information | <60
3 | Governance and Policy | 3.1.1 Legal and customary framework | >80
|  | 3.1.2 Consultation, roles and responsibilities | 60-79
|  | 3.1.3 Long term objectives | Not scored
| Fishery specific management system | 3.2.1 Fishery specific objectives | >80
|  | 3.2.2 Decision making processes | >80
|  | 3.2.3 Compliance and enforcement | <60
|  | 3.2.4 Management performance evaluation | 60-79